## PROCESS_INDICATORS
[11 empty] | PI_CODE_FREEZE |  |  | PI_TEST_EXEC |  | PI_TEST_PASSED |  | PI_TEST_AUTO
[11 empty] | < |  |  | < |  | < |  | <
[11 empty] | 5% |  |  | 5% |  | 5% |  | 5%
[11 empty] | 15% |  |  | 15% |  | 15% |  | 15%
[11 empty] | 30% |  |  | 30% |  | 30% |  | 30%
[11 empty] | 40% |  |  | 40% |  | 40% |  | 40%
[11 empty] | 100% |  |  | 100% |  | 100% |  | 100%
[5 empty] | Project Database |  |  |  |  | 1 |  | Test plan / Test report
Visible | Forecast | Site | Product | Release | Code Freeze date | Release date | Freeze period (WORK DAYS) | Total FTEs | # Issues fixed | Effort (WORK DAYS) | % Effort | planned | executed | % not executed | passed | % not passed | automated | % manual
TRUE |  | HBO | iFast | iFast v5.3 | 2017-03-15 | 2017-03-31 | 12 | 3 | 6 | 6 | 16.67% | 152 | 152 | 0% | 152 | 0% | 0 | 100%
TRUE |  | HBO | iFast | iFast v6.0 | 2017-12-08 | 2017-12-22 | 10 | 3 |  | 0 | #NAME? | no data | no data | #VALUE! | no data | #VALUE! | no data | #VALUE!
TRUE |  | HBO | Maps | Maps 3.2 | 2017-06-08 | 2017-07-03 | 17 | 10 | 46 | 46 | 27.06% | 750 | 750 | 0% | 750 | 0% | 5 | 99.33%
TRUE |  | HBO | Maps | Maps 3.3 | 2017-10-27 | 2017-11-10 | 10 | 10 |  | 0 | 0% | no data | no data | #VALUE! | no data | #VALUE! | no data | #VALUE!
TRUE |  | HBO | Data Services | Data Services 4.2 | 2016-10-30 | 2016-12-14 | 32 | 5 | 23 | 23 | 14.37% | 1831 | 1819 | 23300% | 1819 | 0.6554% | 1388 | 24.19%
TRUE |  | HBO | Data Services | Data Services 4.3 | 2017-03-01 12:00 | 2017-03-31 12:00 | 22 | 5 | 7 | 7 | 6.364% | 1859 | 1842 | 0.9145% | 1842 | 0.9145% | 1415 | 23.88%
TRUE |  | HBO | Data Services | Data Services 4.4 | 2017-05-16 | 2017-06-15 | 22 | 5 | 0 | 0 | 0% | 1861 | 1839 | 1.182% | 1839 | 1.182% | 1413 | 24.07%
TRUE |  | HBO | Data Services | Data Services 4.5 | 2017-11-24 12:00 | 2017-12-08 12:00 | 10 | 5 |  | 0 | 0% | no data | no data | #VALUE! | no data | #VALUE! | no data | #VALUE!
TRUE |  | HBO | Data Services | Data Services 4.6 | 2017-11-29 12:00 | 2017-12-13 12:00 | 10 | 5 |  | 0 | 0% | no data | no data | #VALUE! | no data | #VALUE! | no data | #VALUE!
TRUE |  | HBO | Metrios | Metrios SW3.1 | 2017-10-30 12:00 | 2017-11-13 12:00 | 10 | 7 |  | 0 | 0% | no data | no data | #VALUE! | no data | #VALUE! | no data | #VALUE!
TRUE |  | HBO | Metrios | Metrios 3.0.2 | 2017-03-20 12:00 | 2017-04-03 12:00 | 10 | 6 | 8 | 8 | 13.33% | 104 | 104 | 0% | 102 | 1.923% | 0 | 100%
TRUE |  | HBO | Tool Readiness | Tool Readiness 1.0 | 2017-12-08 12:00 | 2017-12-22 12:00 | 10 | 4 |  | 0 | 0% | no data | no data | #VALUE! | no data | #VALUE! | no data | #VALUE!
FALSE |  | EDV | Velox | Velox 1.2.0 | 2016-03-25 12:00 | 2016-04-08 12:00 | 10 | 19 | 38 | 38 | 20% |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | Velox | Velox 1.2.1 | 2016-07-08 12:00 | 2016-07-22 12:00 | 10 | 19 | 15 | 15 | 7.895% |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | Velox | Velox 1.2.2 | 2016-09-01 12:00 | 2016-09-15 12:00 | 10 | 26 | 7 | 7 | 2.692% |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
TRUE |  | EDV | Velox | Velox 1.3.0 | 2016-10-14 12:00 | 2016-10-28 12:00 | 10 | 19 | 54 | 54 | 28.42% | 73 | 69 | 5.479% | 59 | 19.18% |  | 100%
TRUE |  | EDV | Velox | Velox 1.4.0 | 2017-01-09 | 2017-01-23 | 10 | 19 | 102 | 102 | 53.68% | 74 | 70 | 5.405% | 62 | 16.22% |  | 100%
TRUE |  | EDV | Velox | Velox 2.0.0 | 2017-04-06 | 2017-04-20 | 10 | 19 | 95 | 95 | 50% | 109 | 105 | 3.67% | 90 | 17.43% |  | 100%
TRUE |  | EDV | Velox | Velox 2.1.0 | 2017-06-30 | 2017-07-14 | 10 | 19 | 65 | 65 | 34.21% | 129 | 127 | 1.55% | 118 | 8.527% |  | 100%
TRUE |  | EDV | Velox | Velox 2.2.0 | 2017-10-06 12:00 | 2017-10-20 12:00 | 10 | 19 |  | 0 | 0% | 138 | 130 | 5.797% | 107 | 22.46% |  | 100%
FALSE | forecast | EDV | Velox | Velox 2.3.0 | 2018-01-05 12:00 | 2018-01-19 12:00 | 10 | 26 |  | 0 | 0% |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | Velox | Velox 2.4.0 | [5 empty] | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | EPU | EPU 1.7.0 | 2016-03-25 12:00 | 2016-04-08 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | EPU | EPU 1.7.1 | 2016-06-17 12:00 | 2016-07-01 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | EPU | EPU 1.8.0 | 2016-10-12 | 2016-10-26 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | EPU | EPU 1.8.1 | 2016-12-30 12:00 | 2017-01-13 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
TRUE |  | EDV | EPU | EPU 1.9.0 | 2017-03-31 12:00 | 2017-04-14 12:00 | 10 | 8 | 20 | 20 | 25% | 77 | 76 | 1.299% | 76 | 1.299% | 0 | 100%
TRUE |  | EDV | EPU | EPU 1.9.1 | 2017-06-30 12:00 | 2017-07-14 12:00 | 10 | 8 | 30 | 30 | 37.5% | 80 | 49 | 38.75% | 49 | 38.75% | 0 | 100%
TRUE |  | EDV | EPU | EPU 1.10.0 | 2017-09-29 | 2017-10-27 | 20 | 8 |  | 0 | 0% | 80 | 78 | 2.5% | 78 | 2.5% | 0 | 100%
FALSE |  | EDV | Tomography | Tomo v4.3.0 | 2016-03-25 12:00 | 2016-04-08 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | Tomography | Tomo v4.3.1 | 2016-06-17 12:00 | 2016-07-01 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | EDV | Tomography | Tomo v4.4.0 | 2016-10-12 | 2016-10-26 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
TRUE |  | EDV | Tomography | Tomo v4.4.1 | 2017-01-06 12:00 | 2017-01-20 12:00 | 10 | 1 | 6 | 6 | 60% | 46 | 38 | 17.39% | 36 | 21.74% | 0 | 100%
TRUE |  | EDV | Tomography | Tomo v4.5.0 | 2017-03-31 12:00 | 2017-06-09 12:00 | 50 | 1 | 2 | 2 | 4% | 65 | 43 | 33.85% | 42 | 35.38% | 0 | 100%
TRUE |  | EDV | Tomography | Tomo v4.6.0 | 2017-09-29 12:00 | 2017-10-27 12:00 | 20 | 2 |  | 0 | 0% | 93 | 7 | 92.47% | 5 | 94.62% | 0 | 100%
TRUE |  | BRN | Auto Slice & View | Auto Slice & View 4.0 | 2016-03-17 12:00 | 2016-03-31 12:00 | 10 | 1 | 0 | 0 | 0% | 42 | 41 | 2.381% | 41 | 2.381% | 2 | 95.24%
TRUE |  | BRN | Auto Slice & View | Auto Slice & View 4.0.1 | 2016-05-20 12:00 | 2016-06-03 12:00 | 10 | 2 | 0 | 0 | 0% | 40 | 38 | 5% | 38 | 5% | 2 | 95%
TRUE |  | BRN | Auto Slice & View | Auto Slice & View 4.1 | 2016-12-01 12:00 | 2016-12-15 12:00 | 10 | 2 | 0 | 0 | 0% | 38 | 37 | 2.632% | 37 | 2.632% | 3 | 92.11%
TRUE |  | BRN | Auto Slice & View | Auto Slice & View 4.2 | 2017-11-02 12:00 | 2017-11-16 12:00 | 10 | 3 | 0 | 0 | 0% | 38 | 38 | 0% | 38 | 0% | 5 | 86.84%
TRUE |  | BRN | VolumeScope | VolumeScope 1.3.1 | 2016-03-08 | 2016-03-22 | 5 | 1 | 0 | 0 | 0% | 23 | 23 | 0% | 23 | 0% | 2 | 91.3%
FALSE |  | BRN | VolumeScope | VolumeScope 1.3.2 | 2017-01-17 | 2017-01-31 | 5 | 1 | 0 | 0 | 0% | no data | no data | #VALUE! | no data | #VALUE! | no data | #VALUE!
TRUE |  | BRN | VolumeScope | VolumeScope 1.4.0 | 2017-05-17 | 2017-05-31 | 5 | 1 | 0 | 0 | 0% | 27 | 27 | 0% | 26 | 3.704% | 2 | 92.59%
TRUE |  | BRN | VolumeScope | VolumeScope 2.0 | 2017-11-01 | 2017-11-15 | 10 | 5 | 20 | 40 | 80% | 27 | 27 | 0% | 27 | 0% | 2 | 92.59%
TRUE |  | BRN | AutoTEM | AutoTEM 4.0 | 2017-03-10 12:00 | 2017-03-24 12:00 | 10 | 3 | 0 | 0 | 0% | 21 | 20 | 4.762% | 20 | 4.762% | 2 | 90.48%
TRUE | Forecast | BRN | AutoTEM | AutoTEM 4.1 | 2017-09-01 | 2017-09-15 | 10 | 4 | 5 | 10 | 25% | 25 | 25 | 0% | 25 | 0% | 5 | 80%
TRUE |  | BRN | Public API | AutoScript 4.0.0 | 2017-12-01 12:00 | 2017-12-15 12:00 | 10 | 3 | 0 | 0 | 0% | no data | no data | #VALUE! | no data | #VALUE! | no data | #VALUE!
FALSE |  | BOD | Amira | Amira 6.1 | 2016-02-16 | 2016-03-01 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Amira | Amira 6.2 | [5 empty] | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Amira | Amira 6.4 | 2017-05-22 | 2017-06-05 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Amira | Amira 6.3 | 2017-01-27 | 2017-02-10 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Amira | Amira 6.5 | 2017-11-13 | 2017-11-27 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE | forecast | BOD | Amira | Amira 6.6 | 2018-06-01 12:00 | 2018-06-15 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Avizo | Avizo MS 9.2 | 2016-06-06 | 2016-06-20 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Avizo | Avizo MS 9.3 | 2017-01-27 | 2017-02-10 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Avizo | Avizo 9.4 | 2017-05-22 | 2017-06-05 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE | forecast | BOD | Avizo | Avizo 9.6 | 2018-06-01 12:00 | 2018-06-15 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | PerGeos | PerGeos 1.0 | 2015-11-01 12:00 | 2015-11-15 12:00 | 9 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | PerGeos | PerGeos 1.1 | 2016-11-16 12:00 | 2016-11-30 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | PerGeos | PerGeos 1.5 | 2017-04-17 12:00 | 2017-05-01 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | PerGeos | PerGeos v1.7 | 2017-09-18 12:00 | 2017-10-02 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | PerGeos | PerGeos 2.0 | [5 empty] | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | PerGeos | PerGeos 2.1 | [5 empty] | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Inspect3D | Inspect3D 4.1.1 | 2016-03-24 12:00 | 2016-04-07 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Inspect3D | Inspect3D 4.1.2 | 2016-09-19 12:00 | 2016-10-03 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Inspect3D | Inspect3D 4.1.3 | 2017-01-17 12:00 | 2017-01-31 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Inspect3D | Inspect3D 4.2 | 2017-04-17 | 2017-05-01 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Inspect3D | Inspect3D 4.3 | 2017-12-01 12:00 | 2017-12-15 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Open Inventor | Open Inventor 9.7 | 2016-12-17 | 2016-12-31 | 9 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Open Inventor | Open Inventor 9.7 Medical Edition (C++) | 2017-03-24 | 2017-04-07 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Open Inventor | Open Inventor 9.8 | 2017-09-01 12:00 | 2017-09-15 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE | forecast | BOD | Open Inventor | Open Inventor 9.9 | 2018-06-01 12:00 | 2018-06-15 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE | forecast | BOD | Open Inventor | Open Inventor 10.0.0 | 2018-04-06 12:00 | 2018-04-20 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE | forecast | BOD | Open Inventor | Open Inventor 10.1 | 2018-11-02 12:00 | 2018-11-16 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE | forecast | BOD | Avizo Core Tech | Avizo Core Tech 9.6 | 2018-06-01 12:00 | 2018-06-15 12:00 | 10 |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
FALSE |  | BOD | Avizo Core Tech | Avizo Core Tech 10 | [5 empty] | 0 | #DIV/0! |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
Formulas:
Code Freeze date = [Release date]-16
Freeze period (WORK DAYS) = NETWORKDAYS([Code Freeze date],[Release date])-1
Note on F9: Perquin, Reinier:Triage date and Release date
Note on K9: Perquin, Reinier:Estimated number of days per fixed issue